## REGIONAL (hidden)
CERRO CORONA
ASSESSMENT: CERRO CORONA Q2 2012 RISK REGISTER
| 10 | [10 empty] | No | Risk Description | Risk Mitigating Action | Rating | P | S
Severity | 9 | [10 empty] | 1 | Social conflicts/blockades (mining industry) | - Comply with commitments - Anticipate potential Conga conflicts / Contingency plan - Monitor key stakeholders and clear communications with stakeholdes | 80 | 10 | 8
| 8 | [10 empty] | 2 | Secure LOM waste storage capacity at CC | - Identify appropiate land for waste storage - Acquire and prepare placement areas | 70 | 7 | 10
| 7 | [10 empty] | 3 | Delivery / Execution of Growth Projects | - Review and develop sequencing and scheduling of projects at CC - Chucapaca Value Engineering / exploration campaign - Salares Norte: exploration campaign + water rights | 63 | 7 | 9
| 6 | [10 empty] | 4 | Government / Political instability | - Lobby / Dialogue with authorities. - Active participation at SNMPE and Chambers of Commerce. | 56 | 7 | 8
| 5 | [10 empty] | 5 | Secure LOM tailings storage capacity at CC | - Tomas reservoir / social license with Manuel Vasquez Association - Design, permitting and construction of Tomas Wing Dam (TWD) - Vira Vira reservoir development | 50 | 5 | 10
| 4 | [10 empty] | 6 | Water management / manage perceptions of communities | - Implement water communication program for communities - Full compliance with EIA and water permits + regulation/standards | 45 | 5 | 9
| 3 | [10 empty] | 7 | Increase in regulatory scrutiny / delays in permitting (Peru / Chile) | - Constant monitoring and strict compliance with regulations - Lobby authorities in Peru and Chile to shape permitting process | 42 | 6 | 7
| 2 | [10 empty] | 8 | Erosion of Free Cash Flow (price volatility/cost inflation/decreasing grades) | - Ensure delivery of Production Plan - Strict cost containment plan - Closely monitor capital projects | 36 | 4 | 9
| 1 | [10 empty] | 9 | Tax contingencies ($30M potential) at GFLC | - Timely respond to all information requests. - Develop defense strategy. - Tax planning to avoid future contingencies | 30 | 5 | 6
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | Stringent Tax Legislation/Regulation | - Lobby with SNMPE - Detailed analysis of potential impact of new regime for GF | 30 | 5 | 6
Probability
P - Probability
S - Severity
[12 empty] | No | Risk Description | Risk Mitigating Action | Rating | P | S
[12 empty] | 1 | Social conflicts/blockades (mining industry) | - Comply with commitments - Anticipate potential Conga conflicts / Contingency plan - Monitor key stakeholders and clear communications with stakeholdes | 80 | 10 | 8
[12 empty] | 2 | Secure LOM waste storage capacity at CC | - Identify appropiate land for waste storage - Acquire and prepare placement areas | 70 | 7 | 10
[12 empty] | 3 | Delivery / Execution of Growth Projects | - Review and develop sequencing and scheduling of projects at CC - Chucapaca Value Engineering / exploration campaign - Salares Norte: exploration campaign + water rights | 63 | 7 | 9
[12 empty] | 4 | Government / Political instability | - Lobby / Dialogue with authorities. - Active participation at SNMPE and Chambers of Commerce. | 56 | 7 | 8
[12 empty] | 5 | Secure LOM tailings storage capacity at CC | - Tomas reservoir / social license with Manuel Vasquez Association - Design, permitting and construction of Tomas Wing Dam (TWD) - Vira Vira reservoir development | 50 | 5 | 10
[12 empty] | 6 | Water management / manage perceptions of communities | - Implement water communication program for communities - Full compliance with EIA and water permits + regulation/standards | 45 | 5 | 9
[12 empty] | 7 | Increase in regulatory scrutiny / delays in permitting (Peru / Chile) | - Constant monitoring and strict compliance with regulations - Lobby authorities in Peru and Chile to shape permitting process | 42 | 6 | 7
[12 empty] | 8 | Erosion of Free Cash Flow (price volatility/cost inflation/decreasing grades) | - Ensure delivery of Production Plan - Strict cost containment plan - Closely monitor capital projects | 36 | 4 | 9
[12 empty] | 9 | Tax contingencies ($30M potential) at GFLC | - Timely respond to all information requests. - Develop defense strategy. - Tax planning to avoid future contingencies | 30 | 5 | 6
[12 empty] | 10 | Stringent Tax Legislation/Regulation | - Lobby with SNMPE - Detailed analysis of potential impact of new regime for GF | 30 | 5 | 6
[12 empty] | 11 | Environmental / ARD seepage risks at CC | - Monitor discharge points. - Ensure compliance with TSF and blankets design; MPL & ECAs | 24 | 3 | 8
[12 empty] | 12 | Delays in construction of the TSF/UCB/blankets at CC | - Monitor progress against schedule. - Ensure availability of equipment and required construction material. | 24 | 3 | 8
[12 empty] | 13 | Land Acquisition - potential restriction to build LVUs and for future growth at CC | - Acquire posesion land and houses in the La Hierba area - Monitor potential seepage - Acquire buffer areas | 24 | 4 | 6
[12 empty] | 14 | Labor legislation / Loss of outsourcing | - Monitor changes in labor legislation - Dialogue and strong lobby with Central government | 20 | 4 | 5
[12 empty] | 15 | Talent Retention | - Implement robust talent management and retention programs | 20 | 4 | 5
[12 empty] | 16 | MRM Reconciliation Issues (potential reduction of LOM) at CC | - Ore flow reconciliation action plan - GTS team audit of models / technical support | 16 | 2 | 8
[12 empty] | 17 | Union / Labour conflicts | - GF to follow up labour union agreements | 10 | 2 | 5
[12 empty] | 18 | Concentrate Theft at CC | - Permanent review of controls and security systems. - Permanent monitoring of road from Cajamarca to the port. - Systematic audit to TRC standards. | 10 | 2 | 5
[12 empty] | 19 | F/X losses - Balance Sheet impact | - Review F/X exposure and implement measures to reduce it | 10 | 2 | 5
[12 empty] | 20 | Potential blasting restrictions at CC | - Ensure remediation of damaged houses by SENCICO. - Work closely with government authorities | 0 | 0 | 0
[12 empty] | 21 | Delivery / Execution of Sulfide Plant Expansion and Oxides Projects | - Review and develop sequencing and scheduling of projects. - Anticipate overlaps and interferences. - Review Project Execution Plans - integrate oxides and sulphides | 0 | 0 | 0
11
2
3
4
5
6
7
8
9
10

## MR Estrategicos 10x10 CC
|  |  |  | REGISTRO DE RIESGO ESTRATÉGICO |  |  | U.E.A. CAROLINA I CERRO CORONA
Código: SSYMA-P02.18-F01
Versión: 01
Fecha de aprob.: 06/08/2024
CERRO CORONA
ASSESSMENT: CERRO CORONA Q4 2023 STRATEGYC RISK REGISTER
|  | No | Risk Description | Impact | Risk Mitigating Action | Rating | Owner | Action Plan
|  | 1 | EIA 9 and operational permits disapproval caused by social, political and regulatory context in Peru (applicability of the Supreme Decree that approves the Regulation of Law No. 31211, Law that provides for the adaptation of transportation and final disposal of tailings to companies that carry out mining-metallurgy activities.) making impossible to extend LoM to 2030 . | Impact | Continuous engagement with regulators that will evaluate EIA 9. Development and application of social and communication strategy with key stakeholders. Stakeholders monitoring . Continuous coordination between GF team. Strict quality control of EIA to reduce observations. Internal and external communications plan. Application of the new legislation in Peru D.S.N° 006-2023-MINAM to request that the regulator applies the previous legal framework for EIA. | 89 | Edwin Zegarra | 0
Severity |  | 2 | Considerable increase in expectations and requests for services, labor and social project opportunities by the populations of the Area of Direct Influence, due to the process of closing the operation (work fronts) could trigger protests, blockades and paralyze the mining operation and intrusion / invasion in our property. | Road blockades (external and internal) Stoppage of operation activities | * Permanent meetings with leaders and stakeholders of the Hualgayoc district and communities/ hamlets in the Area of Direct Influence to inform, socialize, raise awareness and monitor their expectations. * Manage and implement new opportunities (business and labor) on the different fronts of the operation. * Dissemination with the authorities of the surrounding populations explaining the activities of the mine closure process. * Manage and implement projects through the multi-stakeholder strategy at different levels of government (local, regional and national). * Before a protest must be in the mine legal, social and security team together. | 76 | Henry Rojas | 0
|  | 3 | Production losses due to unstability in the pit and interaction phases in mining activities (conditions: end of mine life, pit bottom and heavy rains). | 0 | *The planned production of the plan should include these risks each month. *Conduct weekly inspection of team leaders and implement operational control. *Continuous monitoring with radars. | 60 | Daniel Roca/Luis Villegas/Julio Torres | 0
|  | 4 | Cost increased due to world wide inflation mainly diesel price and potential additional cost derivated from "El Niño" phenomenom. | As of February, an additional cost of US$ 8M has been projected for 2022 year, using current prices. | Optimization of main mine activitities such as: hauling distances, explosives consumption among others. Review of all contracts scope, mainly which expires. Prioritization of consultants and services. Limitation of travels and expenses. Frequent monitoring of commotitties prices impact. Approval of unbudget activities only if are been offset. | 47 | Rafael Caballero | 0
|  | 5 | Loss of talent by LOM from the mine and external options. | 0 | Identification of key personnel, mapping of contribution and potential. Retention proposals. | 47 | Fabio Escobar | 0
|  | 6 | Delay of the authority in the granting and/or renewal of licenses and permits, due to the high turnover of officials and unqualified personnel, in the institutions that approve the permits. | Operating without permits exposes GFLC to the risk of fines and/or downtimes. | Monitoring and control of the Licenses and Permits table. Management and permanent review of the operational permits schedule. Permanent contact with the operational areas. Constant interaction with the authority before and during the processing of the permit. | 47 | Ines Nuñovero | 0
|  | 7 | Cyber attack. | Systems and information being compromised can affect the normal Operation and Reputation of GF | Antimalware tool running on every laptop, desktop and server. Network analyticsto to detec any suspicious activity. Secure Internet access banning risky web sites. VPN remote access with double factor authentication . Security Case managament practice. Back up and Replication Strategy. | 46 | Jose Ishikawa | All mitigating actions has been completed: * Antimalware tool running on every laptop, desktop and server * Network analyticsto to detec any suspicious activity. * Secure Internet access banning risky web sites. * VPN remote access with double factor authentication * Security Case managament practice * Back up and Replication Strategy
|  | 8 | Work stoppage due to the process of progressive separation of workers from contractors, especially MUR WY, due to the progressive reduction of mining work and reduction of services of contracting companies in general in Cerro Corona. | Stopping the production process | *Review of essential positions. *Each critical area must develop a contingency plan. *Maintain active communication with contractor management. *The MUR administration must implement a workers' exit plan | 44 | Fabio Escobar | 0
|  | 9 | Shortage of strategic supplies - explosives due to global logistics crisis and conflict in Europe. | Disruption in mine operations due to reduction in blasting capacity | Long term contract renewed with Orica, sourcing of base nitrate moved away from Russia. In-country stock level by vendor increased to 90 days. Continuous monitoring with Orica for early detection of potential supply issues. | 43 | Jorge Luis Garcia | 0
|  | 10 | Material Failure in the Open Pit. | 0 | * Competence of geotechnical personnel. * Specialized technical area. * QA/QC. * Geotechnical monitoring instruments: (Radar, Robotic Station, Extensometers, Piezometers, Clinometers). * SOP Analysis (Care of slopes due to blasting). * Pre- and post-blasting checklist. * Drain control superficial / underground. * Controlled blasting (Pre-split). * Design review by external consultant. * Equipment calibration. * Competence of Perforation and Blasting personnel and supervision. * Instrumentation. * Specific study of pit/dam earthquakes. * Ensure the reliability of the Network (Communications System). * Hydrological monitoring (pluviometer) * Emergency Response Plan. * Evacuation Plan due to Geotechnical Alert or Earthquake in Mine Operations. * Safety signage and walls. | 37 | Julio Torres | 0
|  | No | Risk Description | Impact | Risk Mitigating Action | Rating | Owner | Action Plan
|  | 1 | EIA 9 and operational permits disapproval caused by social, political and regulatory context in Peru (applicability of the Supreme Decree that approves the Regulation of Law No. 31211, Law that provides for the adaptation of transportation and final disposal of tailings to companies that carry out mining-metallurgy activities.) making impossible to extend LoM to 2030 . | * Impossibility to extend LoM to 2030 (current approved LoM is up to 2025) | Continuous engagement with regulators that will evaluate EIA 9. Development and application of social and communication strategy with key stakeholders. Stakeholders monitoring . Continuous coordination between GF team. Strict quality control of EIA to reduce observations. Internal and external communications plan. Application of the new legislation in Peru D.S.N° 006-2023-MINAM to request that the regulator applies the previous legal framework for EIA. | 89 | Edwin Zegarra
|  | 2 | Considerable increase in expectations and requests for services, labor and social project opportunities by the populations of the Area of Direct Influence, due to the process of closing the operation (work fronts) could trigger protests, blockades and paralyze the mining operation and intrusion / invasion in our property. | Road blockades (external and internal) Stoppage of operation activities | * Permanent meetings with leaders and stakeholders of the Hualgayoc district and communities/ hamlets in the Area of Direct Influence to inform, socialize, raise awareness and monitor their expectations. * Manage and implement new opportunities (business and labor) on the different fronts of the operation. * Dissemination with the authorities of the surrounding populations explaining the activities of the mine closure process. * Manage and implement projects through the multi-stakeholder strategy at different levels of government (local, regional and national). * Before a protest must be in the mine legal, social and security team together. | 76 | Henry Rojas
|  | 3 | Production losses due to unstability in the pit and interaction phases in mining activities (conditions: end of mine life, pit bottom and heavy rains). |  | *The planned production of the plan should include these risks each month. *Conduct weekly inspection of team leaders and implement operational control. *Continuous monitoring with radars. | 60 | Daniel Roca/Luis Villegas/Julio Torres
|  | 4 | Cost increased due to world wide inflation mainly diesel price and potential additional cost derivated from "El Niño" phenomenom. | As of February, an additional cost of US$ 8M has been projected for 2022 year, using current prices. | Optimization of main mine activitities such as: hauling distances, explosives consumption among others. Review of all contracts scope, mainly which expires. Prioritization of consultants and services. Limitation of travels and expenses. Frequent monitoring of commotitties prices impact. Approval of unbudget activities only if are been offset. | 47 | Rafael Caballero
|  | 5 | Loss of talent by LOM from the mine and external options. |  | Identification of key personnel, mapping of contribution and potential. Retention proposals. | 47 | Fabio Escobar
|  | 6 | Delay of the authority in the granting and/or renewal of licenses and permits, due to the high turnover of officials and unqualified personnel, in the institutions that approve the permits. | Operating without permits exposes GFLC to the risk of fines and/or downtimes. | Monitoring and control of the Licenses and Permits table. Management and permanent review of the operational permits schedule. Permanent contact with the operational areas. Constant interaction with the authority before and during the processing of the permit. | 47 | Ines Nuñovero
|  | 7 | Cyber attack. | Systems and information being compromised can affect the normal Operation and Reputation of GF | Antimalware tool running on every laptop, desktop and server. Network analyticsto to detec any suspicious activity. Secure Internet access banning risky web sites. VPN remote access with double factor authentication . Security Case managament practice. Back up and Replication Strategy. | 46 | Jose Ishikawa | All mitigating actions has been completed: * Antimalware tool running on every laptop, desktop and server * Network analyticsto to detec any suspicious activity. * Secure Internet access banning risky web sites. * VPN remote access with double factor authentication * Security Case managament practice * Back up and Replication Strategy
|  | 8 | Work stoppage due to the process of progressive separation of workers from contractors, especially MUR WY, due to the progressive reduction of mining work and reduction of services of contracting companies in general in Cerro Corona. | Stopping the production process | *Review of essential positions. *Each critical area must develop a contingency plan. *Maintain active communication with contractor management. *The MUR administration must implement a workers' exit plan | 44 | Fabio Escobar
|  | 9 | Shortage of strategic supplies - explosives due to global logistics crisis and conflict in Europe. | Disruption in mine operations due to reduction in blasting capacity | Long term contract renewed with Orica, sourcing of base nitrate moved away from Russia. In-country stock level by vendor increased to 90 days. Continuous monitoring with Orica for early detection of potential supply issues. | 43 | Jorge Luis Garcia
|  | 10 | Material Failure in the Open Pit. |  | * Competence of geotechnical personnel. * Specialized technical area. * QA/QC. * Geotechnical monitoring instruments: (Radar, Robotic Station, Extensometers, Piezometers, Clinometers). * SOP Analysis (Care of slopes due to blasting). * Pre- and post-blasting checklist. * Drain control superficial / underground. * Controlled blasting (Pre-split). * Design review by external consultant. * Equipment calibration. * Competence of Perforation and Blasting personnel and supervision. * Instrumentation. * Specific study of pit/dam earthquakes. * Ensure the reliability of the Network (Communications System). * Hydrological monitoring (pluviometer) * Emergency Response Plan. * Evacuation Plan due to Geotechnical Alert or Earthquake in Mine Operations. * Safety signage and walls. | 37 | Julio Torres
|  | 11 | Illegal mining activity increases considerably in Hualgayoc, which generates a climate of insecurity and limits the growth of potential projects |  | Close coordination with local, regional and national authorities Continuity of the inter-institutional cooperation agreement with the National Police Promote and manage interdiction in risk areas Permanent monitoring of the situation in the Area of ​​influence. Support for Projects in the area of ​​influence and Monitoring of information before and during potential Projects Human Rights Action Plan. | 37 | Antonio Rios Pita Alvaro Arce
|  | 12 | Changes in the regulatory framework that affect compliance with the mining plan for ore extracted from the PIT according to LOM 2030 (legal requirements, permitting, schedule, administrative sanctioning processes in case of breaches, etc) | Delays in permit management. Changes or increase in sanctions' regulations, environmental standards, supervision's criteria, etc that increase operational costs. | Keep timely meetings with authorities and communities. Special contact must be kept with their Dialogue and Social Management Bureau to track social conflicts within Cerro Corona area. Monitor regulatory changes from the Executive Branch, as well as from Congress through the Chamber of Mines. | 25 | Domingo Drago
|  | 13 | Potential increase of COVID - 19 Pandemic cases due to new variants and failure of upcoming government to contain the virus. | High morbidity and high absence of workers in the mine. Loss of man-hours work/production. Sanitary uncertainty in the workers who attend the mine. Fear of workers for infecting their families. Potential increase in mortality. | Mine Recovery Plan . Protocols & facilities implemented Vaccination of all workers with a booster dose. External advice from expert doctors. Early detection of suspected cases with PCR / Antigen Test. Permanent surveillance of the sanitary protocol to enter, during stay and to leave the mine. Early primary medical care of positive cases of workers and family members. | 4 | Fabio Escobar
|  | 14 | Increase of taxes in mining due to Peru´s Fiscal , economic and social context, added to the promises made during the election campaign. Other regulatory proposals against mining continue to be a risk | Tax increase to the mining sector. Potential changes in the "social licence" regulation. Implementation of the "land use planning" framework. | Strengthen the company’s participation and relationship with the sector’s trade union (SNMPE) Prepare a coordinated plan with the SMPE to facilitate the defense against potential regulatory risks Propose a pro-active strategy of reforms, not just a reactive strategy Strengthen the public relations strategy that showcases mining as a key element for Peru´s economy | 4 | Domingo Drago
|  | 15 | New regulation on the Outsourcing of Services: Legal prohibition of entrusting GF's nuclear activities to a third party company. | Incorporation to the Gold Fields (GF) payroll of all the workers of contractor companies that provide services in Cerro Corona in activities that qualify as nuclear GF (core business according to new criteria of the national regulation). | Initiation of legal actions that question the validity and applicability of the new regulation for being contrary to the Law of Outsourcing and Constitution of Peru, and prevent the incorporation of headcount of contractors. Contractual delimitation of services provided by contractors that could qualify as nuclear activities to limit the potential headcount that could be included in the GF form. General review of efficiencies in headcount of contractors to reduce the potential risks of incorporation to the GF payroll. Evaluate services that can be provided outside of Cerro Corona (avoid displacement of personnel). Communicational strategy to mitigate social, labor and union claims, with special emphasis on community workers. | 0 | Fabio Escobar | Various impact scenarios have been evaluated and designed based on the associated risk fronts: economic, legal, social, NPV, reputational, union, operational (stoppages), in order to ensure that the one that best mitigates the identified risks is chosen.
16
|  | 9 | Shortages of drinkable water for the Cerro Corona camp and community due to delayed relocation of the Coymolache treatment plant and delayed arrival of components for the pre-treatment system. |  | Look for options to shorten the acquisition and installation time of pre-treatment equipment to start its operation as planned by Engineering and Construction. Supply of water by cisterns from the area of Cobro to the Definitive PTAP. Water rationalization campaign in the camp. | 43 | Edwin Zegarra
|  | 13 | Potential increase of risk related to fire detection |  | Siemmens fire Detection System is in End Of Life. Electronic cards are difficult to replace. Inability Of firmawre updates to resolve bugs and keep optimal System calibration
|  | 14 | Loss of visual control based CCTV around concentrate chain transportation |  | Axis CCTV system is in End of Life. Recording system is out of support Inability Of firmawre updates on cameras

## matriz RE
Severity | 10
| 9 | [6 empty] | 1
8
| 7 | [6 empty] | 2
| 6 |  |  |  | 4,5,6 |  | 3
| 5 |  |  |  |  | 7
| 4 |  |  |  |  | 10 | 8
| 3 | [7 empty] | 9
2
1
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Probability

## Sheet2 (hidden)
Risk Description | Risk Mitigating Action | Rating | P | S
Social conflicts/blockades - Conga crisis | - Comply with commitments - Anticipate potential Conga conflicts / Contingency plan - Monitor key stakeholders and clear communications with stakeholders | 72 | 9 | 8
La Hierba Land Acquisition - potential restriction to build LVUs | - Acquire posesion land and houses in the area - Monitor potential seepage | 56 | 7 | 8
Appropiate Waste Storaging areas | -Identify appropiate land for waste storage purpose. -Acquire and prepare placement areas. | 42 | 6 | 7
Increase in regulatory scrutiny/ EIA | - Constant monitoring and strict compliance with regulations - Follow up and dispute sanctioning processes with regulator | 36 | 6 | 6
SMCG Union - labour conflicts | -SMCG to negotiate with forming Union. GF will Follow up & support close. | 35 | 7 | 5
Restriction to raise tailings above the Tomas Spring level | - Tomas reservoir / social license with Manuel Vasquez Association - VIRA VIRA reservoir & Develop Wing Dam | 35 | 5 | 7
Government instability | -Lobby / Dialogue with authorities -Active participation at SNMPE and Chambers of Commerce | 30 | 6 | 5
Talent Retention | - Implement robust talent management and retention programs | 24 | 6 | 4
Labor legislation / Loss of outsourcing | - Monitor changes in labor legislation - Dialogue and strong lobby with Central government | 21 | 3 | 7
Erosion of Free Cash Flow (price/cost variability) | - Ensure delivery of Production Plan - Strict cost containment plan - Closely monitor capital projects | 20 | 4 | 5